## Sofra
Sofra Tasks Schedule for Web Training
Week 1
Database analysis |  | TRUE
WebService analysis |  | TRUE
General Apis | about 13-14 service | TRUE
Week 2
Client Auth Cycle Apis |  | TRUE
Restaurant Auth Cycle Apis |  | TRUE
Restarant Food Items Apis |  | TRUE
Restarant Offers Apis |  | TRUE | لسه الاشعار للعملاء
Week 3
Client Order Cycle Apis | includes Review for restaurant | TRUE
Restaurant Orders Apis |  | TRUE
Settings Api |  | TRUE
Restaurant commissions Api |  | TRUE
Week 4
Admin dashboard analysis |  | TRUE
Prepare AdminLte for our project |  | TRUE
Dashboard home page | includes simple statistics | TRUE
Cities module |  | TRUE
Regions/Districts module |  | TRUE
Categories module |  | TRUE
Week 5
Restaurants Payments module | list&filter - create - edit - delete | TRUE
Offers Module | list&filter - delete | TRUE
Contacts module | list&filter - delete | TRUE
Settings module | only edit | TRUE
Payments module |  | TRUE
Week 6
restaurants module | list&filter - show - delete - activate - deActivate | TRUE
payemntMethods module |  | TRUE
clients module | list&filter - delete - activate - deActivate | TRUE
orders module | list&filter - show&print | TRUE
Week 7
users module |  | FALSE
roles module |  | FALSE
Automated Check Permission Middleware |  | FALSE
change password page |  | FALSE